Process for RUE Committee

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| **Process Step** | ➊  GATHER DATA  Research | ➋  DEFINE | ➌  GENERATE IDEAS | ➍  REFINE | ➎  BUILD | ➏  PILOT |
| **Goal** | Understand needs of stakeholders | Define objectives for undergrad. Ed. | Identify ways of accomplishing objectives. | Evaluate ideas and select best ones for further development. | Develop specific undergrad experiences. | Test experiences and gather data |
| **Time (wks)** | 8 | 4 | 4 | 8 | 8-? | 2019-20 |
| **Tasks** | - Get info from:  Students  Alumni  Faculty  Administration  Employers  State (USHE, Legislature)  Other institutions  (Surveys, panels, focus groups etc.)  - Previously published research  - Identify important constraints.  Institutional  (student demographics, facilities, personnel, costs, commuter campus, etc.)  USHE | - State problems with current system.  - Identify opportunities for improvement.  - What undergrad. Ed. should do. | - Current ideas:  FYE Seminar  HIPs  Degree Pathways  - Other institutions  - Conferences  - Papers  - Unique ideas | - Identify method for applying constraints and explore feasibility  - Systematically review ideas | - Create framework  - Develop curriculum  - Determine budget  - Identify stewardship  - Audience/subjects | - Gather necessary approvals  (administration, grants, curriculum etc.)  - Run pilot tests of experiences  - Collect data  - Analyze and assess results  - Refine  - Iterate |
| **Outcome/ Deliverables** | - Report including summary of methods, data collected, results and conclusions for each stakeholder group.  - Process description for how to collect data. | - Report and presentation of |  |  | - Proposal containing blueprint and framework for piloting. |  |
| **Audience/ Review/ Approval** |  |  |  |  |  |  |